## Sheet1
HREiR Action plan template (January 2021-December 2023)
Details
| Institution name: | University of Hertfordshire | The institutional audience* for this action plan includes :
| Cohort number: | 2 | Audience |  | Comments
| Date of submission: | 11.12.2020 | Research staff | 137 | 346 staff submitted for the REF
Postgraduate researchers
|  |  | Research and teaching staff | 1112 | Not all of these staff will be research-active
|  |  | Technicians | 112
|  |  | Professional support staff | 1095
Other (please provide numbers and details):
2456
Column1 | Obligation2 | Action | Success Meaure (SMART) | Deadline | Responsibility | Progress upadate (to be completed for submission) | Outcome/result | Action carried over from previous action plan?
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | The Concordat features in all RDG Meetings and is featured on Researcher Development webpages (internal and external). RC and PRMG are kept up to date with work of RDG and progress with action plan for HREiR Award. The Concordat will feature in opening talk at #UHResDev21 from Chair of RDG to all research active staff. Staff will be informed that we are signatories of the new Concordat through RO News. The benefits of institutional membership of Vitae will be shared through input at #UHResDev21 by a representative from Vitae, through the RDP and RDG. The Concordat and Vitae will be included in new research staff induction checklist. | 100% of researchers completing CEDARS have some understanding of the Concordat to Support the Career Development of Researchers or know it exists | 2021-09-01 | Chair of RDG; RDG; RDP; HR; RO |  |  | 7.2
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | HR are reviewing all policies and will conduct an equality impact assessments (EIA) on all amendments and on all new HR or equality University Policies and Regulations (UPRs) to help ensure they are inclusive, equitable and transparent. Close cooperation between HR, EO, and RDG will help communicate these policies to researchers and their managers. | HR complete the review of policies and ensure they are inclusive, equitable and transparent. Updated policies available on HertsHub for all researchers and their managers to access. HR representaive on RDG alerts member to any changes and where these policies can be found. | 2021-12-01 | HR; RDG |  |  | Yes 1.2
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | Establish staff network for mens' mental health chaired by Director of Estates. Promote mental health awareness workshops. #UHResDev21 keynote on mental health and wellbeing of researchers. New RDP sessions are generic to both PGR and ECR, with an emphasis on wellbeing directly or indirectly. Target ECRs with advertising to raise their awareness and attendance. Establish an EDI board to look at EDI priorites for UH and provide a reporting body for EDI data to identify issues that need to be addressed; including ensuring researchers and research managers are attending the mandatory EDI training; and responding to CEDARS to ensure that the culture of diversity and inclusion is developed further. Support equity through development of cross university system for workload management. | 80% of researchers attend mandatory/refresher EDI training (REC target); 70% of researchers completing CEDARS agree or strongly agree that their working environment supports their mental health and wellbeing; 80% of researchers completing CEDARS agree or agree strongly that UH will investigate any reported incident of discrimination, or of bullying and harassment fairly; 80% trust that UH would take appropriate action if appropriate after such an investigation | Sep-21; | EO; HSW; RDG; RDP; ? |  |  | Yes 2.3; 6.2
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | Mandatory attendance reports of EDI training will be reviewed by the Deans to share with the line managers in schools. This has been trialled with one school. | 80% of staff completion of mandatory training | 2021-04-01 | L&OD |  |  | 2.3; 6.1; 6.2; 6.3; 6.4
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | All research staff who are also research students have mandatory training in research integrity. We will explore the possibility of redesigning this training and rolling out to ECRs, along with refresher training for other researchers. A gap analysis of the new Concordat for Research Integrity is underway, and any new areas highlighted will be addressed as part of the action plan for the Research Integrity Concordat | 70% of researchers completing CEDARS have undertaken Research Integrity training. 50% of managers of researchers completing CEDARS have undertaken Research Integrity training; 80% of researchers completing CEDARS trust UH to investigate any reported incidents of research misconduct fairly; 80% trust that UH would take action if appropriate after such an investigation | 2021-09-01 | RDP; Susan Grey |  |  | N/A
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | Procedures for research integrity are clearly set out in UPR RE02 Research Misconduct and reviewed annually by Research Committee. Increase participation of researchers completing CEDARS through effective timing and marketing of the survey, using the outcomes to improve practices through a review and development process involving Research Committee and RDG) | 100% increase in researchers completing CEDARS (260 responses; 54 responses for PIRLS in 2019 and 75 responses for CROS in 2019) | 2021-09-01 | L&OD; RDG; RC |  |  | 7.1; 7.2
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | All Managers will have an EDI action on racial equality and awareness-raising . EDI for managers workshop to be run bimonthly to capture all line managers to update their awareness of their responsibilities along with three yearly refresher training on Equality and Diversity and Unconscious Bias. | 70% of researchers completing CEDARS agree or strongly agree that staff are treated fairly irrespective of any protected characteristics. 80% ofline managers have completed their mandatory and refresher training | 2021-06-01 | EO; line managers |  |  | 6.1; 6.2; 6.3; 6.4
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | Research integrity is included in the training for research supervisors. We will explore the possibility of refresher training for experienced researchers. The 2021 PGR conference will have a keynote from James Parry of UKRIO. | 50% of managers completing CEDARS have undertaken training on research integrity; 70% of researchers completing CEDARS agree or strongly agree that their manager supports them to develop their research integrity | 2022-09-01 | RDP; Susan Grey |  |  | N/A
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | Establish staff network for mens mental health chaired by Director of Estates. Promote mental health awareness workshops. #UHResDev21 keynote on mental health and wellbeing of researchers. Introduction of an EDI board to look at EDI priorities for UH and provide a reporting body for EDI data to identify issues that need to be addressed. Establish an EDI board to look at EDI priorites for UH and provide a reporting body for EDI data to identify issues that need to be addressed; including ensuring researchers and research managers are attending the mandatory EDI training and responding to CEDARS to ensure that the culture of diversity and inclusion is developed further. | 80% of researchers attend mandatory/refresher EDI training (REC target); 70% of managers completing CEDARS feel confident to respond to any issues relating to health and wellbeing; and to any issues relating to bullying and harassment. More than 70% of researchers completing CEDARS agree or strongly agree that their manager promotes a good worklife balance | Sep-21; | EO; HSW: RDG |  |  | Yes; 2.3; 6.1; 6.2; 6.3; 6.4
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | All managers attend the mandatory HR Policies in practice. This will be monitored and reported to the EDI board. | 80% of managers completing CEDARS feel confident to manage requests for flexible working appropriately; 0% of researchers completing CEDARS disagree or disagree strongly that they are treated fairly in relation to requests for flexible working | 2021-09-01 | L&OD |  |  | N/A
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | The Research Committee (RC) chaired by the Pro-Vice Chancellor for Research provides opportunities for consultation with research managers to communicate their views on both internal policy and decisions as well as external initiatives, such as implementing the new concordat. The RDG acts also as a consultative group for RC, gathering researcher and research manager views through school representatives, survey analysis and circulation of minutes to all ADRs and other research managers | Minutes of RC and and RDG meetings showing where research managers' views have be sought on policy development and acted upon. Analysis of research surveys to show where research managers' views have contributed to policy development and resulted in a more positive research environment and culture. | 2021-07-01 | RC, RDG; ADRs; PIs |  |  | N/A
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | ADRs encourage researchers to buddy with or mentor newer researchers and students; enable newer researchers to join research programmes led by experienced researchers; and/or join doctoral supervision teams. | 90% of newer researchers (research active for 0 to 4 years) completing CEDARS agree or agree strongly that they feel included in their immediate research environment/group | 2022-12-01 | ADRs |  |  | N/A
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | We will explore the possibility of redesigning the research integrity training and rolling out to ECRs, along with refresher training for other researchers, to increase awareness and attendance by researchers who have not completed the training as research students. Researchers and research managers complete the mandatory EDI training to ensure that the culture of diversity and inclusion is developed further. | 80% of researchers completing CEDARS have undertaken Equality, diversity and inclusion training. 70% of researchers completing CEDARS have undertaken Research integrity training. 60% are familiar with UH's mechanisms to report incidents of misconduct and 60% would feel comfortable reporting any incidetns of research misconduct | 2022-09-01 | L&OD; Susan Grey; RDP |  |  | N/A
ECR3 | Take positive action towards maintaining their wellbeing and mental health | #UHResDev21 will focus on how researchers can be proactive in looking after themselves, and support those they work with and supervise, with respect to mental health and wellbeing, raising awareness of signs to look out for in ourselves and each other. The EAP will be signposted at #UHResDev21 | More than 50% of researchers completing CEDARS agree or strongly agree that they take positive action to maintain their mental health and wellbeing | 2021-06-01 | RDG |  |  | N/A
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | Explore possibility of redesigning the research integrity training and rolling out to ECRs, along with refresher training for other researchers, to increase awareness and attendance by researchers who have not completed the training as research students. Researchers and research managers complete the mandatory EDI training to ensure that the culture of diversity and inclusion is developed further. | 70% of researchers completing CEDARS have undertaken Research integrity training; 60% of researchers completing CEDARS agree or strongly agree that they are familiar with my institution’s mechanisms to report incidents of discrimination, or of bullying or harrassment; 60% of researchers completing CEDARS agree or strongly agree that they would feel comfortable reporting an incident of discrimination or of bullying or harrassment | 2022-09-01 | L&OD; RDP |  |  | 6.1; 6.2; 6.3; 6.4
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | ECRs from all Schools actively engage in RDG, to provide their voice in institutional policy and decision-making through RDG Chair reporting to RC. Researchers participate in research surveys and staff surveys adding their voice to how well policy and practice are working and the impact on the environment and culture. | Attendance and engagement of ECRs with RDG activities and RDG minutes. Analysis of reserch and staff surveys evidencing where researcher views ave impacted policy, environment and culture. | 2021-12-01 | ECRs; RDG; RC |  |  | N/A
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | HR has implemented anonymous shortlisting and made the diversity of recruitment panels, particularly ethnic diversity, mandatory. HR also offer advice for positive action wording of adverts. | 80% researchers completing CEDARS agreed or strongly agreed their recruitment, selection and appointment was fair, inclusive, transparent and merit-based | 2021-09-01 | HR; EO |  |  | 1.1
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | Take forward the positive lessons learnt through moving induction on-line, in order to maintain wider attendance of researchers. Update researcher induction checklist through working with RDG, ADRs and PIs. | 80% researchers completing CEDARS found their induction very useful or useful at institutional level; school level and local to their current role | 2021-09-01 | HR; ADRs; PIs; RDG |  |  | 1.2
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | The process for academic promotions has been enhanced with a more diverse Dean’s panel, to include both a female and BAME members, and specific feedback against the criteria for unsuccessful applicants. Specific workshops have been run for Female applicants and BAME applicants led by the Deputy Vice Chancellor. For Researchers generic job descriptions exist for Research Assistant, Senior Research Assistant, Research Fellow and Senior Research Fellow to ensure consistency in grading against responsibilities and clear pathways for progression. | The number of promotions to Readers, Assoc. Prof and Prof and the increase in proportion of female professors (currently 38%) incresed BAME promotions. Progress against the KPIs of increasing BAME UH9 and above to 16% and female staff at AM1 and above by 10%. Source: HR/EO. Respondants views on both researcher surveys and staff surveys indicating processes are clear and transparent . | 2021-10-01 | HR; EO |  |  | Yes 1.3
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | Research leaders engage with L&OD in conducting a learning needs analysis and attend subsequent training opportunities | 35 or more researchers responding to request for engagement | 2021-12-01 | L&OD |  |  | 4.2
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | The university operates annual appraisals and six monthly reviews with all appraisers undertaking mandatory training. There is also a workload allocation model in existence for all academic roles which does vary slightly from school to school. The HR system has been upgraded and now provides and opportunity to bring both appraisal and workload allocation online and the benefits of this are being explored. HR has made ethnicity and gender diversity on both promotion and recruitment panels mandatory in order to increase the diversity of staff. | The results of exploring an online version of appraisal which would allow managers to monitor completion rates and L&OD to see a holistic view of learning needs. The results of exploring the benefits of an online work allocation model which would provide more consistency across the schools. Progress on the KPIs of increase of BAME staff at UH9 and above to 16% and increase of female staff at AM1 and above by 10%. | 2021-11-01 | HR; EO |  |  | Yes 1.2; 1.3
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | HR concluded in 19/20 there was no requirement for bridging funding as most researchers with transferable skills move to support other research areas or undertake work as Visiting Lecturers between fixed term contract. This will continue to be monitored as will the number of fixed term contracts, though they do relate to funding arrangements. HR will be reviewing all policies on a rolling basis over 20/21 and any changes will be communicated via Herts Hub. | Monitor use of fixed term contracts for researchers and via HR representative on RDF and CEDARS. Policies updates available on HertsHub for all researchers and their managers to access | 2021-12-01 | HR |  |  | Yes, 1.1
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | The Research Committee (RC) chaired by the Pro-Vice Chancellor for Research provides opportunities for consultation with all researchers to communicate their views on both internal policy and decisions as well as external initiatives, such as implementing the new concordat. The RDG acts also as a consultative group for RC, gathering researcher and research managers' views through school representatives, survey analysis and circulation of minutes to all ADRs and other research managersReview opportunities that researchers and their managers have to engage with development of organisational policies and decision-making. Report findings to RC. | Minutes of RC and and RDG meetings showing where all researchers' views have be sought on policy development and acted upon. Analysis of research surveys to show where all researchers' views have contributed to policy development and decision making | 2021-07-01 | RDG; RC |  |  | N/A
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | There is a programme of mandatory workshops that all line managers must complete along with Supervision training. There are also three yearly refresher training requirements for recruitment, unconscious bias, equality and diversity and health and safety. The L&OD team are undertaking a projet to review to content and deivery method of all madatory and refresher training and how to monitor completion more effectively. | 80% of line managers completed and up to date with mandatory and refresher training. | 2021-09-01 | L&OD |  |  | 1.2
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | Complete all line manager mandatory workshops, particulalry HR policies in pracrice, Appraiser and Recruitment and Selection; bespoke and regular grant funding workshops available to Schools; and managers to attend funding workshops run by RO as appropriate. | 80% of line managers completed and up to date with mandatory and refresher training and having attended appropriate grant funding | 2021-09-01 | RO; L&OD |  |  | 1.2
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Complete all line manager mandatory workshops, particulalry Rescruitment and Selection and Appraiser and Successful People Management | 80% of line managers completed and up to date with mandatory and refresher training. 70% of researchers completing CEDARS agree or strongly agree that their manager support them in working towards promotion opportunities | 2021-09-01 | L&OD |  |  | 1.3
EM4 | Actively engage in regular constructive performance management with their researchers | Complete all line manager mandatory workshops, particularly Appraiser and Successful People Management | 100% of researcher managers completing CEDARS have undertaken training on conducting appraisals. More than 90% of researcher managers completing CEDARS are confident or fully confident in their ability to manage appraisal processes effectively. More than 50% of researchers completing CEDARS found their appraisal useful or very useful. 80% of line managers completed and up to date with mandatory and refresher training. | 2021-09-01 | L&OD |  |  | 1.2
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | The Research Committee (RC) chaired by the Pro-Vice Chancellor for Research provides opportunities for consultation with research managers. The RDG acts also as a consultative group for RC, gathering researcher and research managers' views through school representatives, survey analysis and circulation of minutes to all ADRs and other research managers. Focus groups are regulalry held after survey data has been analysed to gain further understanding of the results and consider actions to address issues. | Minutes from RC and RDF and CEDARS results confirming managers are able to contribut towards decision making orpolicy development | 2021-07-01 | RDG; ADRs; PIs |  |  | N/A
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | Researchers attend all mandatory and refresher training | 80% of researchers attend mandatory/refresher EDI training (REC target); 50% attend RO training. | 2021-09-01 | RO; EO |  |  | N/A
ER2 | Understand their reporting obligations and responsibilities | Researchers attend all mandatory training | 80% of researchers attend H & S training | 2021-09-01 | HSW |  |  | N/A
ER3 | Positively engage with performance management discussions and reviews with their managers | Researchers complete appraisal preparation form and return to line manager prior to appraisal meeting | 70% of researchers completing CEDARS agreed or strongly agreed that their immediate manager clearly articulates their expectations of me with respect to my role and performance | 2021-09-01 | OVC; ADRs; line managers; researchers |  |  | 1.2
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | RDG raise awareness within Schools of review of how researchers engage with policy and decision-making in the institution | 40% of researchers completing CEDARS expressed an interest in, or have participated in institutional policy and decision-making | 2021-09-01 | RDG; School reps. |  |  | N/A
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | Raise awareness of Research and Scholarly Time UPR, which includes a minimum of 10 days for professional development. Ensure Research and Scholarly Time and professional development forms part of appraisal discussions through appraisal guidance and Appraiser and Successful People Management (A&SPM) training. Provoke discussion and provide guidance to broaden appreciation around the nature of effective professional development through RDG and RDP. Request funding to reinstate Skill Up! in 2021. | 70% of researchers completing CEDARS have spent 10 or more days on training and other CPD activities; Skill Up! rounds to take place in 2021. | 2021-12-01 | L&OD; RDG; RDP; HR; OVC |  |  | Yes; 1.2; 2.2; 3.1; 3.2; 4.1
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | Offer a careers workshop in #UHResDev21 and raise awareness to researcher managers of careers advice for their researchers and the appraisal guidance documents that provide advice on careers guidance. | 80% of managers completing CEDARS felt confident to actively support their researchers in working towards their career aspirations | 2021-07-01 | RDG; Careers & Employment; HR |  |  | 1.2
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | Offer a careers workshop in #UHResDev21 and raise awareness of careers advice for researchers on careershub and Vitae. | 80% of researchers completing CEDARS agree that they are aware of the support their institution provides for their career and professional development | 2021-07-01 | RDG; Careers & Employment |  |  | 3.1
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | Ensure clear and transparent information on mentoring schemes is available on HertsHub and this is brought to the attention of researchers and their managers. Provide mentor training centrally, and monitor the development of the mentoring schemes through encouraging coordinators to share best practice. Opportunities to develop leadership skills internally and externally are identified and disseminated to researchers. | Internal and external leadership training opportunities are advertised through HertsHub and attended by Research Leaders. Internal and external mentoring opportunities are advertised through HertsHub and taken up by Research Leaders. Information is signposted through RO News, RDG and other internal communications. Attendance on mentor training sessions offered through L&OD | 2021-12-01 | L&OD |  |  | 1.4; 4.1; 4.2; 5.1; 5.2
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | Raise awareness of resources available through UH Careers and Employment, and Vitae, at #UHResDev21 and through RO news | 70% of researchers completing CEDARS agree that their manager encourages them to consider a wide range of future career options within and beyond academia | 2021-07-01 | Careers & Employment; RO |  |  | 3.1
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | Investigate what reports are available on the upgraded HR system; to explore the opportunity to complete appraisals online and allow access to L&OD, to monitor, report on and to tailor provision to specific staff development needs | Report from L&OD shared with RDG and appropriate actions identified | 2021-11-01 | HR; RDG; L&OD |  |  | N/A
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning |  | PCDI2
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Managers are made of aware of the requirement for appraisal to include a career development review through appraisal guidance documentation and A&SPM training which includes signposting resources available through Vitae. | 70% of researchers completing CEDARS have a regular formal career development review with their manager / supervisor (separately or as part of their appraisal) | 2021-09-01 | L&OD |  |  | 3.1
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | RO news includes input from Careers and Employment, to support managers to direct researchers towards appropriate support. Ensure clear and transparent information on mentoring schemes is available on HertsHub and this is brought to the attention of researchers and their managers. Provide mentor training centrally, and monitor the development of the mentoring schemes through encouraging coordinators to share best practice. | 70% of managers completing CEDARS felt confident to actively support their researchers in working towards their career aspirations; 60% of researchers completing CEDARS agree that their manager encourages them to consider a wide range of future career options beyond academia. | 2021-12-01 | Careers & Employment; RO; RDG |  |  | 1.4
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | Provide a guide to the broad nature of professional development activities that researchers can engage with as part of their 10 days | 70% of researchers completing CEDARS agree or strongly agree that their manager encourages them to engage in personal and career development activities | 2021-09-01 | RDG; RDP |  |  | 4.1
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | Actively promote VCAs amongst researcher community and encourage managers to nominate researchers for recognition through the VCA for research success | Increase in number of individual and groups of researchers that are nominated for the VCA for research success; 70% of researchers completing CEDARS agree or strongly agree that their manager supports them to develop their research identity | 2021-06-01 | OVC; ADRs |  |  | Yes; 2.1
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | Actively promote leadership and management training opportunities through websites and internal communications | 50% of researchers completing CEDARS have undertaken, or would like to undertake, leadership and people management training | 2021-09-01 | L&OD |  |  | N/A
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Provide a guide to the broad nature of professional development activities that researchers can engage with as part of their 10 days, including external events such as the Vitae conference, subject specific conferneces or workshops and journal articles. | 70% of researchers completing CEDARS have spent 10 or more days on CPD activities, attendance of at least one person per year at the Vitae conference | 2021-10-01 | RDG; RDP; L&OD |  |  | 4.1; 5.2
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | Raise awareness of resources available through UH Careers and Employment, and Vitae, at #UHResDev21 and through RO news. Raise awareness of mentoring provision through HertsHub page, RDG and RO News. | 90% of researchers completing CEDARS are aware of the support that their institutions provides for their career and professional development. | 2021-07-01 | Careers & Employment; RDG; RO |  |  | 3.1; 3.2; 5.1
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | Raise awareness of RIS and RIS training, through RO news | 70% of researchers completing CEDARS agree or agree strongly that they maintain a formal record of their CPD activities | 2021-09-01 | RO |  |  | N/A
PCDR4 | Positively engage in career development reviews with their managers | Staff update emails remind researchers to complete self assessment and return to line manager prior to appraisal meeting | 70% of researchers completing CEDARS agree or agree strongly that their immediate manager support them in their broader career aspirations | 2021-09-01 | OVC; ADRs; line managers; researchers |  |  | 1.2
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Expand understanding of the breadth of opportunities that lead to effective researcher development through guidance for researchers and their line managers, and through RDP & RDG | 50% of researchers completing CEDARS have undertaken, or would like to undertake, leadership and people management training | 2021-09-01 | RDG; RDP; L&OD |  |  | 4.2
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | Create a broader understanding of the nature of apporopriate professional development activities that researchers can undertake as part of their 10 days. | 50% of researchers completing CEDARS expressed an interest, or have taken up opportunities to engage in knowledge exchange, public policy development, public engagement and commercialisation | 2021-12-01 | RDG; RDP; L&OD |  |  | 5.1; 5.2
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
ADR | Associate Dean (Research) |  | Key
CEDARS | Culture, Employment and Development in Academic Research Survey |  | Gap analysis - new objectives
ECR | Early Career Researcher |  | Action carried forward from last action plan
EO | Equality Office
HSW | Health, Safety and Wellbeing
L&OD | Learning and Organisational Development
MMH | Men's Mental Health
OVC | Office of the Vice Chancellor
PI | Principlpe Investigator
RC | Research Committee
RDG | Researcher Development Group
RDP | Researcher Development Programme
RO | Research Office
UPR | University Policies and Regulations
VCA | Vice Chancellors Awards